## Sheet1
S no. | App | Module | Sub module | Bug description | screenshot | status | severity / priority | comments
1 | admin | login | footer | the text "protected by zinto security" is overlapped by login page | https://prnt.sc/MYmbi4hwhL3i | Closed | low
2 | admin | dashboard | header - notification icon | click on click on notification icon --> scroll --> it scrolls dashboard page instead of notification page |  | Closed | low |  | forgot password functionality
3 | user | splash screen | footer menu | the footer is black in colour it should match with the theme |  | New | low
4 | user | home | select delivery address | remove cross icon as it is not working and not needed --> location is compulsory |  | Closed | low
5 | user | home | select delivery address | if location is off --> it should show a pop to enable mobile phone's location |  | Closed | critical
6 | user | login | click back | it should not show exit app pop up instead it should redirect back to home page |  | Closed | medium
7 | user | login | header | add back icon for back navigation in ios and android |  | Closed | high
8 | user | login | logo on header | the logo of login page is mandatory it should be smiley logo provided by client for app | https://prnt.sc/feTT0rB2k4v1 | Closed | low
9 | user | login | mobile number field | fill saved phone number --> the colour of the field changes to blue --> it should remain white |  | Closed | low
10 | user | login | mobile number field | fill mobile number --> click open terms or privacy policies --> click back --> the previously filled mobile number should not be removed |  | Closed | medium | same in login with email
11 | user | login | fill unregistered number | if phone number is not registered --> it should show validation that phone number is not registered please sign up |  | Closed | critical | imp
12 | user | login | fill mobile number | click continue --> otp page --> click back --> mobile number should not be removed |  | Closed | low
13 | user | sign up | fill details | click open terms or privacy policies --> click back --> it opens login page instead of sign up page |  | Closed | high
14 | user | sign up | fill details | click open terms or privacy policies --> click back --> the previously filled mobile number should not be removed |  | Closed | low
15 | user | sign up | fill details | click continue --> otp page --> click back --> name and mobile number is removed and only email is there --> all three fields should be saved |  | Closed | low
16 | user | sign up | fill details | already registered /login number should not be re- registered --> it should show proper validation | https://prnt.sc/-lPUgQ4Fmwk5 | Closed | critical | validation message should be user friendly
17 | user | sign up | email | same email should not be registered again |  | Closed | critical
18 | user | sign up | mobile number field | Mobile Number field should accept only valid Indian mobile numbers starting with 6 , 7 ,8 , 9 only |  | Closed | high
19 | user | sign up /login | otp page | otp should have timeout functionality set the time limit for otp validation and add a timer there |  | Closed | high
20 | user | sign up /login | otp page | resend otp should work --> the previous otp should not be validate after resend otp |  | Resolved | high
21 | user | login with email | password | remove password field and add otp verification for email login too as we are not making any password in sign up |  | Closed | critical | imp
22 | user | login with email |  | login with email not working |  | Resolved | critical | showing invalid or expired otp
23 | user | whole app | header & footer | status bar and phone navigation should match with page themes |  | New | low
24 | user | home | header | change logo --> add official zinto logo with name beside it |  | Reopen | high | size of logo should be smaller and add name of the app
25 | user | all pages |  | images are not updating anywhere |  | Closed | critical
26 | delivery | join now | terms & privacy | terms & privacy are not clickable |  | Closed | critical
27 | delivery | join now | terms & privacy | terms & privacy should have a mandatory checkbox before completing registration |  | Closed | high
28 | All |  |  | order id should be smaller so that it'll be easy to manage and search orders |  | Reopen | high | in admin done
29 | user | sign up | terms & privacy | there are 2 terms & conditions and privacy policies --> remove one without checkbox |  | Closed | low
30 | user | sign up / login | mobile number | mobile number field should not accept characters , special characters |  | Closed | high
31 | user | sign up / login | otp | deleted account's phone number --> it shows too many otp request and other validation but not able to make new account with same phone number |  | Resolved | critical
32 | user | home | location | shows service unavailable in areas where service is available --> location should be auto fetched after login and after actions | https://prnt.sc/d51K7WLpV_6m | Reopen | critical | still it needs refresh after login
33 | user | all pages | footer | footer menu is overlapping adjust the size according to all screen sizes |  | Closed | medium
34 | admin | customers | search | search icon is overlapping the text behind (placeholder) | https://prnt.sc/0yEqKF21zgXy | Closed | low
35 | admin | customers | search | complete the search label (placeholder) |  | Closed | low
36 | admin | customers | action -> view | customer id should be smaller |  | Closed | medium
37 | delivery | join now | terms & privacy | agree checkbox should be at the last page of registrations instead of all pages |  | Closed | medium
38 | delivery | join now | step 2 | vehicle plate number and driving license number should accept correct format only --> currently they are accepting wrong data |  | Closed | medium
39 | delivery | join now | step 3 | pan card , account number and ifsc code field should accept correct format data only |  | Closed | medium
40 | delivery | join now | step 4 | click register --> while register is in process driver should not be able to change photos |  | Resolved | high
41 | delivery | join now | step 4 | the documents are not submitting as it is showing file size is too large |  | Closed | critical
42 | admin | delivery drivers | active drivers | scroll down --> show nan - nan is mentioned there --> it should shows how rows are there and row limit per page | https://prnt.sc/jxjHe5WaaODq | Closed | low
43 | admin | delivery drivers | active drivers | scroll down --> next button should not get active there is actual data on next page |  | Closed | low
44 | delivery | all pages |  | all pages should open from top --> if one page is scrolled others open from down |  | Resolved | high
45 | user | profile | edit profile | change photo and camera icon is not clickable --> unable to change or upload profile photo |  | Closed | high
46 | user | profile | edit profile | email address --> fill already registered email --> shows wrong(technical) validation --> it should be user-friendly validation that email is already registered |  | Closed | high
47 | user | profile | edit profile | while filling any field ---> footer is coming up with the keyboard --> it should not as it hides field |  | Resolved | medium
48 | user | profile | edit profile | DOB --> should not take future dates as dob |  | Closed | medium
49 | user | profile | saved address | add new address --> phone number should accept 10 digits only - no special character and alphabets |  | Closed | low
50 | user | profile | saved address | add new address -->pin code should accept 6 digits only - no special character and alphabets |  | Closed | low
51 | user | profile | saved address | edit address --> fill wrong address --> it shows technical validation | https://prnt.sc/mr2PGwy0iBdi | Closed | low
52 | user | profile | saved address | edit address --> there should be an option to mark address as default and after marking other address should be unmarked from default --> currently it is selecting first address as default |  | Resolved | high | the default tag still on first address
53 | user | home | header categories | select any header category --> the product of that header category should appear there instead of all products |  | Reopen | critical
54 | user | categories | products | add filters , sort by ,distances filters |  | Closed | high
55 | delivery | home | service status | online --> if driver is not approved it shows same validation on top and bottom | https://prnt.sc/cEo8mVUJpF4Q | Closed | high |  |  | from admin --> make seller and driver
56 | seller | open app | splash screen | there are 2 splash screens --> remove one |  | Reopen | low
57 | user | checkout | header --> share | share on header is not clickable --> remove if not needed |  | Closed | low
58 | user | checkout | slider to place order | slider placeholder should be fully visible |  | Closed | medium
59 | seller | login/ signup |  | login and sign up pages are not scrollable |  | Closed | critical
60 | seller | signup | terms & privacy | terms & privacy are not clickable |  | Resolved | critical | taking to user app now
61 | admin | delivery drivers | waiting for review | if new delivery driver registers and is waiting for reviews admin should get the notification in notification bar on header and red dot or count of menu page |  | Closed | high
62 | admin | header | notification | on clicking notification --> respective page should open |  | Closed | medium
63 | delivery | home | deliveries/ returns | 12% growth is static there it should show 0 initially | https://prnt.sc/LOYqrj5PFtxI | Closed | medium
64 | delivery | home | deliveries | page has static text that says there are 9 pending orders when there is none --> it should be dynamic | https://prnt.sc/hitbGDWt7Bie | Reopen | medium | now it shows 7 order pending
65 | All | toast notifications | all pages | toast notification should come on header instead of footer as they overlap footer |  | Resolved | medium
66 | seller | login/ signup | header | zinto logo is already there remove zinto text and seller partner |  | Closed | low
67 | seller | login/ signup | header - logo | in logo white colour is looking different with background |  | Resolved | low
68 | seller | signup | click back | on clicking back --> should open login page instead of exit app pop up |  | Closed | low
69 | seller | signup | email and phone | if mail or number is already registered it should not show otp field --> currently it is verifying already registered mail and number |  | Closed | critical
70 | seller | under verification page |  | remove "go to home" button as it redirects to user app |  | Closed | critical
71 | seller | under verification page | after verification | page should automatically refresh and open dashboard but needs re login and other actions |  | Closed | high
72 | seller | dashboard | header | zinto logo is overlapped by other elements of header |  | Closed | low
73 | admin | categories | header category | add new header --> apply commission at this level -->fill gst --> if shows not able to make category --> it gst field is empty it'll make category |  | Closed | critical
74 | admin | categories | header category | edit header --> apply commission at this level -->fill numbers --> 0 should be replaced with filled numbers |  | Closed | low
75 | admin | categories | header category | edit header category --> apply commission at this level -->fill gst --> it shows not able to update category --> it gst field is empty it'll update category |  | Closed | high
76 | admin | categories | main category | create category --> shows wrong validation | https://prnt.sc/z9PwhzPaE0Cw | Resolved | high
77 | admin | categories | main category | add any category - upload image make category --> than edit any other category --> the previous category uploaded image is overcoming on new category too |  | Resolved | high
78 | admin | categories | sub category | add any category - upload image make category --> than edit any other category --> the previous category uploaded image is overcoming on new category too |  | Resolved | high
79 | admin | product | add product | header should not overlap add product form |  | Resolved | medium
80 | admin | product | add product | background should not scroll |  | Resolved | medium
81 | user | all pages | become a seller | become a seller should open a static page to take interested candidate data so that admin can contact and a play store link or seller app --> not the whole registration on user app |  | Resolved | critical
82 | user | profile | header | there are 2 same notification icons - one is showing notification other is triggering push notification --> remove trigger |  | Resolved | medium
83 | delivery | profile | all pages | while filling any field ---> footer is coming up with the keyboard --> it should not as it hides field |  | Resolved | medium
84 | delivery | profile | support | chat icon should in centre and text and icon should be same aligned as call support | https://prnt.sc/xNGOce-XQL32 | Resolved | low
85 | delivery | profile | my documents | view file --> gallery photos are zoomed out --> they should open in their real size |  | Resolved | low
86 | delivery | profile | bank account | request change --> all three fields are accepting wrong format |  | Resolved | medium
87 | delivery | profile | all pages | on doing any action 2 toast notifications are coming one top and other at down --> remove down ones |  | Resolved | high
88 | admin | all pages | headers | all headers should be fixed and only body should scroll |  | Resolved | medium
89 | admin | products | add product | not able to make/create products |  | Resolved | critical
90 | admin | products | add product | not able to mark product as future or preorder |  | Resolved | critical
91 | admin | products | add product | remove approved status not needed as products are made by admin only |  | Resolved | medium
92 | admin | products | add product | action - remove accept or reject actions |  | Resolved | medium
93 | admin | menu bar |  | master catalog and catalog bundle are selecting together only one should be selected at once | https://prnt.sc/DejZEgn888Ve | Resolved | medium
94 | admin | master catalog | alternative name | placeholder --> remove hindi text change it to english | https://prnt.sc/0NbVvkjvuSkb | Resolved | low
95 | seller | add shop/store | fetch current location | cancel button is going out of page | https://prnt.sc/QpYd2Bi5Z5vB | Closed | low
96 | seller | add shop/store |  | form should not scroll horizontally |  | Closed | low
97 | seller | add shop/store |  | all fields are accepting wrong input - aadhar , pan , account number etc |  | Closed | low
98 | user |  |  | move phone horizontally --> the footer is changed |  | New | high
99 | user | footer menu |  | from clicking back from any footer menu page --> home page should open |  | Resolved | high
100 | seller | login | home | click back --> login page should not open |  | Closed | critical
101 | seller | shop setup | add new shop | pick store location --> search location not working |  | Reopen | critical
102 | seller | push notification |  | seller should get the push notification when their shops are approved |  | Reopen | high
103 | seller | product | product details | product details should appear in one single card instead of horizontal scrolling |  | Resolved | medium
104 | seller | product | product details | edit --> gallery photos are not updating in photos page |  | Resolved | high
105 | admin | sellers | seller application | invite seller --> the invited seller is not getting mail |  | Reopen | high
106 | admin | sellers | seller application | view invites --> not showing invite history |  | Closed | medium
107 | admin | sellers | create vendor account | email and password should not be autofilled |  | Closed | low
108 | admin | sellers | create vendor account | password field should have eye button to view password |  | Closed | medium
109 |  | invited seller mail |  | change the mail structure grand bazaar in mentioned instead of zinto | https://prnt.sc/vxXfy1xMlCgv | Resolved | high
110 | seller | browse catalog |  | the cards should be square in shape |  | Closed | low
111 | seller | browse catalog | add this product | categories , commission , weight /pack size is not visible on configure listing details |  | Resolved | medium
112 | seller | browse catalog | select multiple product | clone products --> it should ask to set price for all variants |  | Resolved | critical
113 | admin | master catalog | create catalog item | should have fields to add variants |  | Resolved | medium
114 | user | checkout | checkbox | return & exchange policy --> open user app over user app |  | Resolved | critical
115 | user | checkout |  | products should not be added more than stock in that item /variant |  | Resolved | low
116 | user | profile | saved address | add new address --> while adding product it should use precise location from map |  | Resolved | critical
117 | seller | new order |  | new order ring is not ringing outside of the app |  | Reopen | critical
118 | seller | new order pop up |  | pop up should show all details --> total item amount , commission , and total receivable amount |  | Resolved | medium
119 | delivery |  |  | delivery boy should get the new order only after seller packed the order |  | Resolved | critical
120 | seller | orders |  | seller is not able to change status to packed |  | Resolved | high
121 | delivery | new order pop up | pick up location | shows only shop name --> should show proper address of the shop |  | Resolved | medium
122 | delivery | new order pop up |  | should show total distance between shop and user |  | Resolved | medium
123 | seller | orders | view order | header is overlapping order page |  | Resolved | medium
124 | delivery | continue order | chat button | chat button not clickable --> not able to chat with user |  | Resolved | medium
125 | user | order tracking |  | chat and call button not clickable --> not able to call or chat with driver |  | Resolved | medium
126 | user | order tracking |  | delivery driver photo is not updating here |  | Resolved | medium
127 | user | order tracking | bill summary | bill summary should show all charges --> currently showing only item , delivery and total amount |  | Resolved | high
128 | user | order tracking | delivered | invoice is not downloading |  | Resolved | medium
129 | user | order tracking | delivered | need help --> chat --> upload icon --> open camera is opening gallery instead of camera |  | New | low
130 | user | order tracking | delivered | need help --> call us is not clickable |  | Resolved | low
131 | user | order tracking | delivered | need help --> all three issues are not clickable |  | Resolved | low
132 | user | order tracking | delivered | need help --> raise ticket --> call email is not clickable and full number and email should be visible on card |  | Resolved | low
133 | delivery | all pages |  | delivery earnings are not visible on any page |  | Resolved | critical
134 | delivery | history |  | the distance and earning amount is different than new order pop up --> in starting it shows driver will earn 326 from this order but after delivering he got 35 |  | Resolved | critical
135 | delivery | history | view details | showing 0 km distance of delivered order | https://prnt.sc/E6mhq8S0PNDf | Resolved | low
136 | user | home | lowest price ever | not showing all products |  | Resolved | high
137 | user | home / stores | add product to cart | on clicking add --> it should open product detail page from where user can select variant |  | Resolved | medium
138 | user | home / stores | out of stock | if one variant is out stock it should not show whole product as out of stock when there are some variants that are in stock |  | Resolved | high
139 | user | home / stores |  | some products are misbehaving and not adding to cart |  | Resolved | high
140 | user | home / stores | product | product detail --> add all details like description , seller information etc downarrow are opening automatically |  | Closed | low
141 | user | home / stores | product | share --> appzero and grand bazaar should not be mentioned in link or text | https://prnt.sc/3VWRbBqyM325 | Resolved | low
142 | user | home / stores | product | share -->should share play store link if app is not installed and if it is installed it should open exact page shared |  | New | medium
143 | user | home / stores | product | share --> open link --> it shows product unavailable when product is available |  | New | low
144 | delivery | deposit cash |  | make a flow to deposit cash to admin |  | Resolved | critical
145 | seller | delivery policy | scheduled delivery | time fields are overlapping |  | Resolved | low
146 | seller | earnings | total revenue | should show seller total revenue ( total item amount) instead of admin revenue (what user paid |  | Resolved | high
147 | seller | earnings | deductions | remove tax |  | Resolved | medium
148 | seller | earnings | your earning | should show payout amount |  | Resolved | medium
149 | seller | earnings | detailed earnings | next button is going out of page --> the text size of footer should be smaller |  | Resolved | low
150 | user | order tracking |  | remove delivery boy rating from everywhere |  | Resolved | low
151 | seller | products | filter | filter is not clickable and going out of page |  | Resolved | low
152 | user | checkout |  | if one variant is out stock and another one is in stock then another in stock product is not placing order |  | Resolved | critical
153 | user | checkout |  | there are 2 packaging charges --> only one should be applied |  | Resolved | high
154 | user | checkout |  | only important charges should be visible in order summary other should be packed and could be viewed if click on that charge |  | Resolved | low
155 | user | checkout | delivery mode | change --> schedule order should open on same page instead of another page |  | Resolved | medium
156 | user | checkout | delivery mode | schedule -->the slot that is passed should be unclickable |  | Resolved | high
157 | user | track order |  | after placing order --> it show finding rider - searching for delivery partner --> it should show waiting for seller to accept order |  | Resolved | medium
158 | seller | new order pop up |  | you will receive amount should change if user adds product |  | Resolved | medium
159 | user | track order | additem to this order | it should show products whose variants are still in stock |  | Resolved | medium
160 | user | track order |  | order accepted and order received are same working remove order received tracker and add order packed after order accepted and them logistics assigned |  | Resolved | low
161 | seller | stock |  | should show variant name of stocking product |  | Resolved | low
162 | seller | pick up order |  | seller should verify the otp and otp should not be visible on seller |  | Resolved | critical
163 | seller | orders | reject | it shows write reason to cancel but there is no box to write reason |  | Resolved | high
164 | seller | orders | timed out | order gets deleted from everywhere |  | Resolved | critical
165 | user | track order | cancel order | the text is written in hinglish change it to english | https://prnt.sc/SClwRR3LC2gl | Resolved | low
166 | seller | earnings |  | showing wrong packaging charge |  | Resolved | medium
167 | user | track order | cancellation request | the text is written in hinglish change it to english |  | Resolved | low
168 | user | track order | adjust price | user should get the adjust price request by seller |  | Resolved | high
169 | seller | profile | edit | change pin is going out of page | https://prnt.sc/cC470qzEpLuL | Resolved | low
170 | seller | all pages |  | change the ui of the pages --> text is congested and buttons are overlapping everywhere |  | Resolved | high
171 | user | order |  | awaiting customer confirmation is overlapping |  | New | low
172 | seller | order |  | awaiting customer confirmation is overlapping |  | Resolved | low
173 | admin | all pages |  | all pages should open from top --> if one page is scrolled others open from down |  | Resolved | high
174 | user | checkout | online payment | on sliding a slider it gives push notification that order has been placed successfully without completing payment |  | Closed | high
175 | user | home |  | on product card -> store name should be present |  | Resolved | low
176 | delivery | new order |  | shows different amount on new order pop and different in earnings |  | Resolved | high
177 | user | order tracking |  | sometimes otp is not generating |  | Resolved | high
178 | delivery | otp |  | otp should not accept 1234 |  | Resolved | high
179 | seller | return order |  | otp is not generating on return orders for seller |  | Resolved | high
180 | delivery | earnings | recent earnings | shows settled for all amount that are not yet settled |  | Resolved | low
181 | user | profile | order transaction | shows 0 for all orders transaction --> should show order amount , type of order (cod , online , wallet) , paid or pending etc |  | Resolved | high
182 | user | profile | rewards and wallet | my referral --> button is not visible |  | Resolved | low
183 | user | profile | rewards and wallet | my referral --> click button --> share on whatsapp --> it shows half page for some time it should not |  | Resolved | low
184 | user | profile | rewards and wallet | my referral --> click button --> share on whatsapp --> it should share play store and app store link |  | New | low
185 | user | profile | rewards and wallet | my referral --> click button --> share on whatsapp --> in login detail add referral code field |  | Resolved | low
186 | user | profile | rewards and wallet | my referral --> click button --> invite via --> qr code is copying the link instead of qr |  | Resolved | low
187 | user | profile | rewards and wallet | my referral --> click button --> invite via --> mobile should share playstore link |  | New | low
188 | user | profile | rewards and wallet | open any page through clicking a cart --> click back --> it should open previous page instead of profile page |  | Resolved | low
189 | user | profile | rewards and wallet | open any page through clicking a cart --> filter buttons are not visible |  | Resolved | low
190 | seller | dashboard | recent notification | view all should open notification page instead of profile page |  | Resolved | low
191 | seller | dashboard | add store assistant | module permission --> needs horizontal scrolling --> it should show everything on same page |  | Resolved | low
192 | user | Store | view store info | shows - no contact phone --> should show store phone and details |  | Resolved | low
193 | user | home | closed store | closed store products should not appear on home page |  | Resolved | medium
194 | seller | store design |  | the text should be in centre and button should be under text --> fix ui of this page according to phone app |  | Resolved | medium
195 | seller | store design | upload logo | remove is going out of box |  | Resolved | low
196 | seller | all pages |  | while filling any field ---> footer is coming up with the keyboard --> it should not as it hides field |  | New | medium
197 | seller | store design |  | save changes button can be smaller |  | Resolved | low
198 | seller | stock management |  | should show variants stocks too and they should also be adjust from this page |  | Resolved | high
199 | seller | stock management | in stock filter | on click in stock filter page refreshes it should not |  | Resolved | low
200 | seller | stock management | out of stock card | out of stock card is smaller than others --> should be same |  | Resolved | low
201 | seller | all pages |  | not downloading files everywhere |  | New | critical
202 | seller | pre order campaign |  | some fields and their titles are not visible | https://prnt.sc/D0u9-5gR5zDH | Resolved | medium
203 | admin | marketing tools | reward campaign | credit timing should be according to all rewards |  | Resolved | medium
204 | admin | marketing tools | reward campaign | 0 should be replaced with number |  | Resolved | low
205 | admin | marketing tools | reward campaign | many things are static they should be according to all rewards |  | Resolved | medium
206 | admin |  |  | make a separate page for admin earnings with detailed breakdown |  | Resolved | critical
207 | admin | marketing tools | reward campaign | if funding source is seller than seller / shop name dropdown should be there |  | Resolved | medium
208 | admin | marketing tools | reward campaign | if funding source is brand than brand name dropdown should appear |  | New | medium
209 | admin | marketing tools | reward campaign | if funding source is shared then there should be an option to choose seller and than percentage should be asked how much % seller will bear and how much % admin will bear |  | Resolved | medium
210 | admin | marketing tools | reward campaign | define priority and its logic if not needed remove it if needed than write explainable name |  | Resolved | medium
211 | admin | marketing tools | reward campaign | flat discount coupon --> remove max discount cap as it will is same as flat amount |  | Resolved | medium
212 | admin | marketing tools | reward campaign | all types of rewards --> start date should not be set in past |  | Resolved | low
213 | admin | marketing tools | reward campaign | all types of rewards --> end date should not be set in past and should not be before start date |  | Resolved | low
214 | admin | marketing tools | reward campaign | remove budget limits from free delivery rewards |  | New | medium
215 | user | product | click back | it should not show exit app notification instead should redirect to previous page |  | Resolved | medium
216 | user | checkout | rewards | reward campaign coupons are not visible on checkout |  | Resolved | critical
217 | delivery | otp page |  | remove terms and privacy from otp page |  | Resolved | medium
218 | user | categories | all levels | if admin didn't upload any photo --> it should show default photo instead of category name |  | Resolved | high
219 | user | login/signup | terms & conditions | item added in cart should not be visible in terms & conditions |  | Resolved | medium
220 | user | login/signup | otp | getting too many otp expired toast messages together |  | Resolved | high
221 | user | login/signup | otp | timeout functionality is not working correctly - on resend the it timeouts automatically |  | Resolved | high
222 | user | cart | available coupon | if coupon or reward is not assigned to user than those coupon and rewards should be visible to that user |  | New | critical
223 | user | login /signup |  | support centre should be there before user logins (can be on login / signup) as they may need support during login or sign up |  | Closed | critical
224 | admin | sellers | edit sellers | message owner is not working | https://prnt.sc/WA370c8OR9i2 | Resolved | critical
225 | admin | sellers | edit sellers | send alert is not working | https://prnt.sc/EDWEDUeC0wrg | Resolved | critical
226 | admin | sellers |  | when seller is under review - it should show a small pop up in which only name number email should be present - or make a separate page for shop and seller review |  | New | medium
227 | admin | category | header category | add new category --> category name --> add space between name or add big capital letter --> than it can make category |  | Resolved | critical
228 | admin | sellers | seller application | admin should get the notification and a red dot count or this page if new shop registered |  | Resolved | high
229 | admin | sellers | seller application | view -->if more than one header category is chosen by seller --> still shows one category name partner only | https://prnt.sc/kkVkdARW9XPw | Resolved | medium
230 | admin | all pages |  | all pages (categories , catalog etc ) should have default images if admin , seller or delivery does not upload any |  | Resolved | high
231 | seller | manage all store | import catalogue | bundle --> it should show all the products under it too |  | Resolved | critical
232 | seller | product |  | one product is taking too much of space vertically --> align information beside one another so one row can have 2 details |  | Resolved | medium
233 | seller | menu bar | select rejected store | rejected store should not open its dashboard |  | Resolved | critical
234 | user | product | product details | shelf life , country of origin , fssai license are static - not asked from seller they should be dynamic |  | New | medium
235 | user | category |  | the product added by seller is not visible in categories or home page |  | New | critical
236 | user |  |  | commissions are not working correctly |  | Resolved | critical | flow paused - 12/09
237 | user | cart | gst | both gst should be in one row only - also add dropdown for charges |  | New | medium
238 | user | cart | amount | amount is mismatching - total is floating point and total amount is in decimal number |  | New | critical
239 | user | cart |  | slide to place order --> remove ¦ and rupee sign | https://prnt.sc/T72HEjSLrSLd | New | low
240 | user | track order | add item to this order | item images are not updating on this page - and if there no image a default image should be there | https://prnt.sc/qHqOjGDWSqt6 | New | medium
241 | user | track order | add item to this order | add item to order --> the button is overlapping | https://prnt.sc/3w6OiCXc9xAs | New | medium
242 | seller | orders | view | if customers add products after order - it should ask seller acceptance |  | New | medium
243 | user | track order | add item to this order | the items are not showing with commission | https://prnt.sc/y86-cEXe_bDP | New | high
244 | seller | orders |  | change the ui when seller is awaiting customer approval | https://prnt.sc/EaF0esZofDi3 | New | medium
245 | user | track order |  | if seller reduce the order --> it should show proper information about product and quantity | https://prnt.sc/eVi8GH3COhug | New | high
246 | user | home |  | not fetching location - even through device location is on |  | New | critical | flow pauused - 17- 09
247 | seller | products | set price & publish | stock --> 0 should be removed while writing stock |  | New | low
248 | admin | sellers | active sellers | edit details --> save details --> show seller not found |  | New | critical
249 | admin | sellers | active sellers | edit details -->description and location should be present in edit details |  | New | high
250 | user | cart | checkout | on some products --> commission is not applying |  | New | high
251 | seller | new order pop up |  | admin commission for product that is given by user should not be visible to seller --> if commission is applicable on seller level by admin than only commission should be visible |  | New | critical
252 | user | categories | sort by filter | sort by filter are not working correctly - and also they should not be sorted out according to store |  | New | high
253 | user | categories | product | share on header --> on click it gives toast message of item shared successfully even when item is shared on any app |  | New | medium
254 | user | categories | product | filters --> the page is scrolling horizontally because of filters |  | New | medium
255 | user | categories | product | filters --> add necessary filters like price range , brand etc |  | New | medium
256 | user | categories | product | product details --> should show all necessary information provided by seller / admin like brand |  | New | medium
257 | seller | orders |  | status should be visible only at one place --> there are 2 status showing same thing remove one | https://prnt.sc/i0gZT_wTGSsl | New | low
258 | user | home | add product to cart | if availability is turned off by seller --> and user try to add product to cart it misbehaves and shows --> product added to cart and product unavailable toast message together |  | New | high
259 | seller | products | availability | if product is hidden --> availability should turn off automatically and if availability is turned on product should be removed from hidden |  | New | high
260 | seller | products | availability | if product availability is turned off --> product should automatically be hidden --> the two of them should work coordinately |  | New | high
261 | user | push notification |  | if seller adjusts the price by 100 less --> the push notification still show seller demanding extra |  | New | low
262 | user | track order |  | the correct product amount (+ commission amount )should be visible on track order page and invoice and other places |  | New | critical
263 | user | cart |  | if product in cart is hidden or unavailable --> it should show proper validation message in cart that product is unavailable --> currently it removes product from cart until its hidden and if it's unavailable it doesn't fetch location |  | New | critical
264 | seller | orders | view - replacement | the replacement tab should open above view tab --> currently it is opening under view |  | New | medium
265 | user | track order | replacement | instead of #1 or # 2 it should show item name | https://prnt.sc/gOmZFgMAgSdL | New | medium
266 | user | push notification |  | didn't get push notification for replacement |  | New | medium
267 | user | profile | wallet | the button at the end is not fully visible | https://prnt.sc/fWHKmJctqAMv | New | medium
268 | user | profile | wallet | there should be a way to see a refund history |  | New | high
269 | user | signup |  | login page is not scrolling on web |  | New | high
270 | user | login | header | support icon is not visible correctly |  | New | low
271 | user | login | header | support -->chat , raise ticket should work before login --> as user may need help/support regarding login /signup |  | New | medium
272 | user | cart | checkout | if two orders are placing together it shows wrong validation on other user --> multiple users should be able to login and order at the same time |  | New | critical
273 | user | cart | checkout | if item quantity is 1 and the product is present in multiple cart --> it should show validation of out of stock product --> order should be placed only if there is a stock of item |  | New | critical
274 | user | cart | checkout | use wallet amount --> place order --> not able to place order and it shows backend details in toast message | https://prnt.sc/3sT8N_v2TvNg | New | critical
275 | seller | new order pop up / orders |  | order id should be smaller in seller |  | New | medium
276 | seller |  |  | if seller does not accept order in time --> it shows order not found on both user and seller app |  | New | critical | on seller app --> order should go in pending state and in some hour if they don't change status to confirm it should give push notification that order will be cancelled in some time and then cancel and user should get the order cancelled notification - not that order not found
277 | user | cart | checkout | if usage limit of an coupon is reached --> it should not be visible to users |  | New | critical
278 | admin | marketing tools | coupon & promos | if usage limit is reached the coupon should be deactivated automatically on admin |  | New | critical
279 | user | cart | checkout | if usage limit left is 1 and 2 people applied the same coupon than on placing order it should not be showing backend toast message of conflict | https://prnt.sc/evyUuuSF9tCZ | New | critical
280 | user | cart | checkout | place online order --> it shows something went wrong |  | New | critical
281 | seller | orders | change status | if order is not available for acceptable or expired --> it should change the status of the order to cancelled |  | New | medium
282 | seller | profile | profile photo | profile photo and background page is not visible | https://prnt.sc/Yv3RD8Ld-PwO | New | low |  |  | price revision kk bad delivery ko notification nhi aya
283 | user | profile | reward & wallet | my referral --> referral should not be successful until new user registers and complete order | https://prnt.sc/UIcbo26f8aFZ | New | high
284 | user | profile | reward & wallet | my referral --> history --> remove code , friend --> instead of friend user that registers name should be there |  | New | high
285 | user | cart | you might also like | out of stock addons should not be visible on cart |  | New | high
286 | user | cart | you might also like | only product from same store should visible in this section |  | New | high
287 | user | cart | schedule now | schedule 6-9 --> close schedule --> reopen schedule --> the time chosen shows default chosen instead of what user chosen |  | New | low
288 | user | cart | schedule now | place order should not appear here |  | New | high
289 | user | notification |  | getting 2 push notification for each action | https://prnt.sc/30SZRtVkMeqf | New | high
290 | user | home | different location | recommended for you --> stores for different location should not be viisible here |  | New | high
291 | user | home | super ad placement | ads of diiferent location / zone should not be visible here |  | New | critical
292 | user | categories | product | shows service unavailable in areas --> it should show category product is not available |  | New | high
293 | user | categories |  | ccategory that has product in that location should be appeared on top |  | New | high
294 | admin | sellers | active sellers | there should be a dropdown/hierarchy in each seller where all its store and their information is visible |  | New | high
295 | admin |  |  | if commission is edited on categories -->it should be making changes on userr app |  | New | high
296 | admin | marketing tools | reward campaign | add new campaign --> cashback & rewards --> new shop promotion & shop wise commission --> sellers /stores are not visible in dropdown |  | New | high
297 | user |  |  |  |  | New | high
298 | [5 empty] | New | high
299 | [5 empty] | New | high
300 | [5 empty] | New | high