## Requirements Checklist
Zinto — Multi-Vendor Hyperlocal Commerce Platform ¦ Requirements Traceability & Test Checklist
S.No | Requirement | Status | Remarks / Notes
1.1 Product Vision
1 | Support multi-vendor operations | Done
2 | Support multi-city operations | Done
3 | Support hyperlocal commerce workflows | Done
4 | Support large-scale product inventory (lakhs of products) | Done
5 | Support high traffic and scalable architecture | Done
6 | Support category/subcategory-driven catalog management | Done
7 | Support seller subscriptions and commission-based business models | Done
8 | Support advanced order lifecycle management | Done
9 | Support dynamic pricing and charge components | Done
10 | Support search, recommendations, and store discovery | Partial / in progress | recomandations not working for now
11 | Support scheduled/future order workflows | Done
12 | Support refunds, returns, partial cancellations, and replacements | After production
13 | Support admin-driven configurability across platform operations | Done
2.1 Database / Schema / System Design Expectations
14 | Database architecture accommodates present and future functionalities | Done
15 | Support multi-vendor platform architecture | Done
16 | Support multi-city operations | Done
17 | Support lakhs of products in inventory | Done
18 | Support categories and subcategories | Done
19 | Support packaging categories | Done
20 | Support transferable / transaction-based category structures if needed | Done
21 | Support orders / payments / cancellations / refunds / returns / partial cancellation / replacement / complaint workflows | After production
22 | Support coupon / offer / subscription / discount modules | Done
23 | Support future feature additions | Done
24 | Support high traffic load | Done
25 | Support scalable search and discovery | Done | only on user side
26 | Support scalable order management and operational workflows | Done
2.2 Technical Expectations
27 | Loose coupling between modules | Done
28 | Scalable component structure | Done
29 | API-ready models and backend architecture | Done
30 | Secure authentication | Done
31 | Efficient search and API handling | Done
32 | Future extensibility without schema redesign | Done
33 | Support role-based flows across Admin / Seller / Customer / Logistics | Done
3.1 Multi-Vendor Model
34 | Multiple sellers/stores can onboard and sell products | Done
3.2 Multi-City Model
35 | Support multi-city operations with city-wise configurable business rules (commissions, delivery, seller/store operations) | Done
3.3 Hyperlocal Commerce Model
36 | Support hyperlocal/quick commerce with nearby seller/store discovery and short delivery workflows | Done
4.1 Customer Panel / Customer App
37 | Register / login | Done
38 | Browse products and stores | Done
39 | Search products and sellers | Done
40 | Add products to cart | Done
41 | Place orders | Done
42 | Place scheduled/future orders | Done
43 | Track order status in real time | Done
44 | Cancel order under allowed conditions | Done
45 | Raise cancellation request | Done
46 | Request refund / complaint within allowed period | Done
47 | Accept/reject replacement suggestions | Done
48 | Reorder previous orders | Done
49 | Rate/feedback on delivered order | Done
50 | Add seller/store to favourites | Done
51 | View previous orders | Done
4.2 Seller Panel
52 | Login to seller portal | Done
53 | Manage shop/store profile | Done
54 | Add and manage products | Done
55 | Manage product listing | Done
56 | Set product pricing | Done
57 | Manage stock/inventory | Done
58 | Publish future-order / pre-book products | Done
59 | View and process incoming orders | Done
60 | Accept orders | Done
61 | Pack orders | Done
62 | Suggest replacement products | Done
63 | Shift delivery to next day where applicable | Done
64 | Cancel orders with reason | Done
65 | Upload / capture delivery-time proof photo | Done
66 | Manage future-order configuration for selected products | Not Done
67 | View settlement-related data if settlement module is enabled | Not Done
68 | Operate with platform logistics or self-delivery mode based on admin/business rules | Done
4.3 Admin / Super Admin Panel
69 | Create seller/vendor accounts | Partial / in progress
70 | Send seller credentials and app links via email | Not Done
71 | Manage seller onboarding | Partial / in progress
72 | Manage subscription plans | Done
73 | Manage commission configuration | Done | dont have separated commission configuration page --> commission is applied on city , category pages
74 | Manage orders and complete order lifecycle | Partial / in progress | flow is there but not updating on ui
75 | Monitor all orders in super admin panel | Done
76 | Approve cancellation requests | Partial / in progress
77 | Assign logistics after packing | Partial / in progress
78 | Manage homepage configuration | Done
79 | Manage banners, categories, featured products, offers, seller highlights | Partial / in progress | SELLER HIGHLIGHTS?
80 | Manage seller recommendations for offline sellers | Not Done
81 | Configure refunds category-wise | Not Done
82 | Configure odd-hour charges, weather fees, delivery charges, platform charges etc. | Done
83 | Manage advertisements / Super AD placements | Not Done
84 | Configure dynamic sections and platform rules | Not Done
85 | Add/edit seller products on behalf of seller | Done
86 | Manage seller shop setup on behalf of seller | Not Done
87 | View and manage seller settlement and bulk-order settlement, if applicable | removed
5. Seller Onboarding & Vendor Management
88 | Admin can create vendor/seller accounts | Not Done
89 | Vendor login credentials shared through email | Not Done
90 | Seller application link shared through email | Not Done | web link
91 | Admin can manage vendor accounts and seller onboarding process centrally | Not Done
6. Seller Subscription Model & Seller Limitation
92 | Seller can onboard/register up to 30 products under base subscription model | Done
93 | Seller must choose a monthly subscription plan to add more than 30 products | Done
94 | Higher commission levels applied if seller does not choose subscription after allowed product limit | Done
95 | Seller business model configurable as subscription basis or commission basis | Partial / in progress
7. Commission Management System
96 | Dynamic and configurable commission structure | Done
97 | Support city-wise commission | Done
98 | Support shop-wise commission | Not Done
99 | Support category-wise commission | Done
100 | Support sub-category-wise commission | Done
101 | Support product-wise commission | Done
102 | Support sub-product-wise commission | Not Done
103 | Support add-on product-wise commission | Not Done
104 | Support shop-level commission | Not Done
105 | Support additional commission components: user, shop, category, platform commission | Not Done
106 | Seller inputs base price per product | Done
107 | Platform applies commission, GST, packing charges on top of base price | Done
108 | Cart/order-level additional charges: handling fees, platform fees, weather surcharge, odd hours surcharge, delivery charge, platform charges | Done
109 | Commission and its application/control handled by admin/platform, not seller | Done
8. Pricing, Charges, Fee Components & Invoice System
110 | Invoice includes breakup of: product cost, handling fees, GST, delivery fees, bad weather fees, odd hours charges, packaging charges, platform-related charges | Done
111 | Support product-level/category-level charges: commission, GST, packaging charges | Partial / in progress | gst left
112 | Support cart/order-level charges: handling fees, platform fees, delivery charge, weather surcharge, odd hours surcharge, platform charges | Done
113 | Auto-generated GST invoices available for customers | Not Done
114 | Auto-generated GST invoices available for sellers | Not Done
115 | Packaging, handling, delivery, weather-based, odd-hour charges configurable from admin panel | Done
9. Order Timing Rules & Order Placement Restrictions
116 | No order placement allowed after 10 PM | Not Done
117 | Odd-hour delivery support and odd-hour charges configurable from admin panel | Done
10. Packaging Charges & Packaging Logic
118 | Packaging charges vary based on product category, handling requirement, packaging complexity | Done
119 | Schema supports packaging categories / packaging charge logic | Done
11. Product Catalog, Product Rules & Inventory Management
120 | Seller can manage product details, images, description, pricing, stock/inventory, category/store association | Not Done
121 | Product description details managed by seller | Not Done
122 | Out-of-stock products not displayed in customer application | Not Done
123 | System supports time-based category/product availability rules | Not Done
12.1 Super Admin Visibility of Seller Product Listings
124 | Super Admin can view all products listed by each seller | Not Done
125 | Visibility includes seller-wise product listings, product details, status/pricing/category/stock, seller-shop-wise product mapping | Not Done
12.2 Product Entry by Super Admin on Behalf of Seller
126 | Admin can select a seller/store and add products under that seller's shop | Not Done
127 | Admin can enter product details, pricing, category, stock, description, images, listing data | Done
128 | Admin can publish/manage the product listing for that seller | Partial / in progress
12.3 Product Editing by Super Admin
129 | Admin can edit product name/details | Done
130 | Admin can edit product description | Done
131 | Admin can edit product category/subcategory | Done
132 | Admin can edit product pricing | Done
133 | Admin can edit stock/inventory details | Done
134 | Admin can edit product images | Done
135 | Admin can edit product visibility / listing status | Done
136 | Admin can edit future-order related configuration if applicable | Not Done
137 | Admin can edit add-on / mapping / packaging-related product configuration if applicable | Not Done
12.4 Full Shop Setup / Shop Management on Behalf of Seller
138 | Admin can configure/manage shop/store profile details | Not Done
139 | Admin can configure shop banners / shop media / about shop details | Not Done
140 | Admin can configure shop category mapping | Not Done
141 | Admin can configure product listing under the shop | Not Done
142 | Admin can configure commission configuration / business configuration where applicable | Done
143 | Admin can perform seller operational setup needed to make the shop live on platform | Not Done
12.5 Admin Override / Assisted Seller Management Use Case
144 | System supports admin-assisted seller management model (seller self-manage or admin manages on behalf) | Not Done
13. Category & Catalog Structure
145 | Support categories | Done
146 | Support subcategories | Done
147 | Support product categorization | Done
148 | Support shop category navigation | Not Done | ?
149 | Support packaging-related category structures if needed | Done
150 | Category model supports name, image, subcategories, slug | Done
14.1 Search Types Supported
151 | Product search: text/keyword search | Done
152 | Product search: real-time suggestions | Done
153 | Product search: search history | Done
154 | Product search: trending searches | Not Done
155 | Voice search: microphone-based search | Done
156 | Voice search: speech-to-text support | Done
157 | Voice search: interactive listening UI | Not Done
158 | Seller/store search: direct seller search | Done
159 | Seller/store search: search stores directly | Done
160 | Seller/store search: seller-wise product search | Not Done | ?
161 | Category search: search by category | Done
162 | Category search: grid-based category browsing UI | Not Done | ?
163 | Category search: sub-category navigation | Not Done
14.2 Smart Search & Recommendation Layer
164 | Support smart recommendations | Done
165 | Support auto suggestions | Done
166 | Support intelligent product discovery | Done
14.3 Search Results Behaviour
167 | Architecture supports showing search & discovery results, store results, product/category result combinations simultaneously | Not Done | ?
15. Map-Based Search & Discovery
168 | Support searching stores via map | Not Done | ? --> distance wise , city wise
169 | Support map-based banner / discovery use cases in home/store visibility design | Partial / in progress | ?
16. Recommendation, Add-On & Cross-Sell Module
170 | Support intelligent add-on/cross-sell product suggestions (e.g., Umbrella + Torch, Dosa + Chutney) | Not Done
171 | Add-on products supported as a commerce object within pricing/commission/product logic | Not Done
17.1 Store / Shop Section in Customer App
172 | Premium store cards | Done
173 | Store logo | Not Done
174 | Store banners | Done | not on card
175 | Ratings display | Done
176 | Delivery estimates display | Done
177 | Modern animations / gradients | Partial / in progress
17.2 Shop Module Details
178 | Video banner on shop page | Not Done
179 | Shop + YouTube banner display | Partial / in progress | advertisement yes , banner no
180 | Signature products section | Not Done
181 | "About My Shop" section | Done
17.3 Store Model Requirements
182 | Store model supports store details, ratings, operating hours, delivery radius | Done
183 | Consider delivery target expectations of 12-15 minutes (not confirmed as final SLA) | Partial / in progress | ?
18. Seller Logistics Flexibility / Logistics Participation Model
184 | Seller not mandatorily bound to use platform logistics | Done
185 | Support platform-assigned logistics mode | Done
186 | Support seller self-delivery / self-managed logistics mode | Done
187 | Support hybrid / configurable logistics model if required | Done
188 | Admin can configure whether seller uses platform logistics, self-delivery, or both | Not Done
189 | Where platform logistics applicable, admin can assign logistics after seller packing | Not Done
190 | Where seller self-delivery mode, order flow supports seller-managed fulfillment | Not Done
19. Advertisement & Promotional Visibility Module
191 | Support banners for homepage | Done
192 | Support banners for promotional sections | Done
193 | Support banners for store/shop visibility | Done
194 | Support redirect-based banners if needed | Done
195 | Support Super AD / premium advertisement placement module | Done
20. Terms & Conditions / Consent Requirements
196 | Mandatory T&C acceptance during registration/onboarding | Not Done
197 | Mandatory T&C acceptance during checkout | Done
198 | "Accept & Agree" checkbox mandatory wherever T&C acceptance required | Not Done
21.1 Login / Signup Page
199 | Modern authentication UI | Done
200 | OTP verification | Done
201 | Email login | Not Done
202 | Mobile login | Done
203 | Responsive mobile-first design | After production
21.2 Home Page
204 | Search bar | Done
205 | Delivery location | Done
206 | Promotional banners | Done
207 | Trending products | Done
208 | Recommended stores | Not Done
209 | Offers / recommended offers | Done
21.3 Search Features
210 | Text search | Done
211 | Voice search | Done
212 | Search by store | Done
213 | Search by category | Done
21.4 Attractive Store Section
214 | Store section with premium UI, strong discoverability, and engaging design | Done
21.5 Client UI Expectations
215 | Premium UI quality | Done
216 | Search fast and intuitive | Done
217 | Store browsing highly attractive | Partial / in progress
22. Home Page Configuration & CMS-Style Admin Control
218 | Home page sections dynamic and configurable from admin panel | Done
219 | Admin can manage banners | Done
220 | Admin can manage categories | Done
221 | Admin can manage product sections | Done
222 | Admin can manage featured products | Done
223 | Admin can manage offers | Done
224 | Admin can manage seller highlights | Not Done
23.2 Backend Model - Customer Model
225 | Customer model supports full name, email, mobile number, address, location, wishlist, order history | Partial / in progress | done in customer app but not in db
23.2 Backend Model - Cart Model
226 | Cart model supports product references, quantity, pricing, store references | Partial / in progress
23.2 Backend Model - Product Model
227 | Product model supports product details, images, pricing, stock management, category reference, store reference | Done | done in db
23.2 Backend Model - Order Model
228 | Order model supports customer reference, product references, delivery details, payment status | Done | done in db
23.2 Backend Model - Category Model
229 | Category model supports category name, image, subcategories, slug | Done | done in db
23.2 Backend Model - Banners Model
230 | Banners model supports banner images, redirect links, active status, priorities | Done | inside heroconfigs
23.2 Backend Model - Store Model
231 | Store model supports store details, ratings, operating hours, delivery radius | Partial / in progress | operating hour left
23.2 Backend Model - Offer Model
232 | Offer model supports discount details, coupon codes, expiry, usage limits | Not Done
23.2 Backend Model - Transaction Model
233 | Transaction model supports payment method, transaction ID, refund status, payment status | Partial / in progress | payment method , refund status left
23.3 Additional Practical Models Implied
234 | Plan for Seller/Vendor model | Done
235 | Plan for Subscription model | Done
236 | Plan for Commission model | Partial / in progress | not centralized
237 | Plan for Refund model | Not Done
238 | Plan for Complaint model | Not Done
239 | Plan for Wallet model | Done
240 | Plan for Notification model | Done
241 | Plan for Logistics model | Done | named as deliveries
242 | Plan for Seller availability model | Not Done
243 | Plan for Add-on product mapping model | Not Done
244 | Plan for Advertisement / Super AD model | Not Done
245 | Plan for Future Order / Scheduled Product configuration model | Not Done
246 | Plan for Seller settlement model / payout ledger | Done
247 | Plan for Bulk-order settlement tracking model | Not Done
248 | Plan for Admin-assisted shop/product management support structure (mapping/audit) if required | Not Done | ?
24. Order Management – Complete Lifecycle
249 | User gets clear and real-time order status visibility | Not Done
250 | Order status flow: Order Placed | Done
251 | Order status flow: Order Received | Done
252 | Order status flow: Order Accepted | Done
253 | Order status flow: Order Packed | Not Done
254 | Order status flow: Logistics Assigned | Done
255 | Order status flow: Out for Delivery | Done
256 | Order status flow: Delivered | Done
257 | Order status flow: Cancelled | Done
258 | Order status flow: Refund Initiated (if applicable) | Not Done
259 | All status updates visible to user | Not Done
260 | Users can track orders in real time | Not Done
25.1 Order Management - Admin Responsibilities
261 | All orders reflected in Super Admin panel | Done
262 | Admin monitors and manages complete order lifecycle | Done
263 | Admin can update and manage orders | Partial / in progress
264 | Admin assigns logistics after seller completes packing where platform logistics applicable | Not Done
25.2 Order Management - Seller Responsibilities
265 | Seller views incoming orders | Done
266 | Seller accepts and processes orders | Done
267 | Seller packs orders | Not Done
268 | Seller may suggest replacement products | Done | ?
269 | Seller may shift order to next day where applicable | Not Done
270 | Seller uploads/captures delivery-time photo as proof during delivery | Not Done
271 | Seller can cancel order with valid reason | Not Done
272 | Seller fulfills through platform logistics or self-delivery based on configured mode | Done
26.1 Scheduled Orders
273 | Users can place scheduled orders for a future date and time | Done
26.2 Seller Future Order Panel
274 | Seller has dedicated Future Order / Pre-Booking panel to publish future-date products | Not Done
26.3 Future Product Configuration by Seller
275 | Seller can mark product as Future Order / Pre-Book Product | Not Done
276 | Seller can configure future delivery date | Not Done
277 | Seller can configure future delivery window | Not Done
278 | Seller can configure booking availability period | Not Done
279 | Seller can configure applicable delivery duration / scheduling range | Not Done
26.4 Advance Booking Window
280 | Customer can book future-order products in advance up to 1 month only | Partial / in progress | ONE WEEK
26.5 Cart Validation for Future Products
281 | System checks if any cart item has a future sale/delivery date when future-order product added | Not Done | ?
26.6 Mixed Cart Scheduling Rule
282 | If at least one future-order product exists in cart, entire order treated as scheduled delivery order | Not Done
283 | All products in cart/order delivered on future scheduled date/window applicable to that future-order product | Done
26.7 Cart Page as Scheduling Page
284 | Cart page behaves as Scheduling Page when future-order product exists in cart | Done
285 | System shows only valid available future delivery dates for that product/order | Done
286 | Customer allowed to select only seller-configured dates for that future-order product | Not Done
27.1 User Direct Cancellation Rule
287 | User can cancel order before seller accepts it | Done
27.2 Post-Acceptance Cancellation Rule
288 | User cannot directly cancel order after seller acceptance | Done
27.3 Cancellation Request Flow
289 | User can raise cancellation request before logistics assignment | Not Done
290 | Only Admin can approve and cancel order after reviewing request | Done
27.4 Seller/Admin Cancellation
291 | Seller and Admin can cancel orders | Partial / in progress | seller cancel not done
292 | Seller must provide valid cancellation reason | Not Done
28.1 Shift Order to Next Day
293 | Seller can move/shift delivery date to next day if product available but cannot be delivered today | Not Done
28.2 Partial Cancellation
294 | Unavailable products can be cancelled while remaining products continue processing/delivery | Not Done
28.3 Product Replacement Suggestion
295 | Seller can suggest another available product if product unavailable | Done
296 | Replacement ideally same price as original | Done
297 | User can accept or reject replacement | Done
28.4 Partial Fulfillment / Split Availability Handling
298 | Cancel unavailable items and refund the amount | Not Done
299 | Deliver available items | Done
300 | Provide updated delivery timeline for unavailable items | Not Done
301 | Offer replacement product with customer confirmation | Done
28.5 Delivery Extension
302 | Vendor/Seller can extend delivery date if order cannot be fulfilled on planned date | Not Done
29.1 Refund Access Window
303 | Refund and complaint options available only within 24 hours after delivery | Not Done
29.2 Refund Countdown
304 | User sees countdown timer for refund/complaint availability | Not Done
29.3 Category-Based Refund Control
305 | Admin can enable/disable refunds based on product categories | Not Done
29.4 Wallet Refund for Cancelled Items
306 | Amount refunded to customer wallet for cancelled/unavailable items | Not Done
29.5 Refund Types to Support
307 | Support full refund | Done
308 | Support partial refund | Not Done
309 | Support cancellation refund | Not Done
310 | Support wallet refund where applicable | Not Done
29.6 Complaint Management
311 | Complaint option available within same post-delivery allowed window | Not Done
30.1 Seller Settlement Management
312 | Support Seller Settlement module for payout/settlement of seller earnings | Partial / in progress
30.2 Settlement Scope
313 | Settlement considers product selling amount | Not Done
314 | Settlement considers applicable commissions | Not Done
315 | Settlement considers GST/tax components where relevant | Not Done
316 | Settlement considers packaging/handling charges sharing rules if applicable | Not Done
317 | Settlement considers refund deductions | Not Done
318 | Settlement considers partial cancellation adjustments | Not Done
319 | Settlement considers replacement impact, if any | Not Done
320 | Settlement considers platform charges or deductions, if applicable | Not Done
30.3 Settlement Status Tracking
321 | Track settlement status: Pending settlement | Not Done
322 | Track settlement status: Processing settlement | Not Done
323 | Track settlement status: Settled | Not Done
324 | Track settlement status: On hold | Not Done
325 | Track settlement status: Adjusted/deducted due to refund or cancellation | Not Done
30.4 Settlement Rules
326 | Settlement logic configurable: after order delivery | Not Done
327 | Settlement logic configurable: after return/refund window completion | Not Done
328 | Settlement logic configurable: after deduction of platform commission and applicable charges | Not Done
329 | Settlement logic configurable: hold in case of complaint/refund/cancellation dispute | Not Done
30.5 Seller Settlement Visibility
330 | Seller panel shows total payable amount | Not Done
331 | Seller panel shows order-wise settlement amount | Not Done
332 | Seller panel shows commission deductions | Not Done
333 | Seller panel shows settlement history | Not Done
334 | Seller panel shows settlement status | Not Done
30.6 Bulk Order Seller Settlement
335 | Support separate settlement calculation for bulk orders if business rules differ | Not Done
336 | Support bulk order commission / margin rules | Not Done
337 | Support partial fulfillment or partial cancellation impact on seller payout | Not Done
338 | Support settlement adjustment if bulk order delivery happens in multiple stages | Not Done
339 | Admin visibility of bulk order settlement breakdown | Not Done
30.7 Admin Settlement Controls
340 | Admin can view seller settlement summaries | Done
341 | Admin can view order-wise seller payable amount | Done
342 | Admin can apply settlement deductions/adjustments | Not Done
343 | Admin can hold/release settlement | Done
344 | Admin can manage bulk-order settlement cases if applicable | Not Done
31.1 Offline Seller Scenario
345 | User gets suggestions for alternative sellers if seller status offline | Not Done
31.2 Admin Role (Seller Availability)
346 | Admin can manage seller recommendations / alternate seller suggestions | Not Done
32. Notification System
347 | Notify: Order placed successfully | Done
348 | Notify: Seller accepted the order | Done
349 | Notify: Order packed | Done
350 | Notify: Logistics partner assigned | Not Done
351 | Notify: Order out for delivery | Done
352 | Notify: Order delivered | Not Done
353 | Notify: Cancellation updates | Not Done
354 | Notify: Refund updates | Not Done
33.1 Feedback & Rating
355 | Customer can provide order feedback | Not Done
356 | Customer can provide rating / review | Not Done
33.2 Reorder
357 | Customer can reorder previously placed orders | Not Done
33.3 Favourite Seller
358 | Customer can add seller/store to favourites | Partial / in progress
33.4 Previous Orders
359 | Customer can view previous orders / order history | Done
34.1 Frontend Deliverables Discussed
360 | Authentication screens | Done
361 | Home page UI | Done
362 | Search modules | Done
363 | Store discovery pages / attractive store section | Done
34.2 Backend Deliverables Discussed
364 | Database schemas | Done
365 | API-ready models | Done
366 | Relationship definitions | Done
34.3 Action Items Discussed Across MOMs
367 | Finalize scheduled order workflow | Partial / in progress
368 | Implement stock visibility logic | Partial / in progress | ?
369 | Define refund, cancellation, and replacement process | Done
370 | Implement order tracking functionality | Done
371 | Set up vendor onboarding via email | Done
372 | Develop admin order management features | Done
373 | Develop home page UI | Done
374 | Implement search features | Done
375 | Design attractive store section | Done
376 | Create database schemas for discussed models | Done
377 | Define model relationships | Done
378 | Prepare for UI review / schema review / feature prioritization discussions | Done
35. Final Product Owner Summary
379 | Seller onboarding and flexible seller business models | Done
380 | Dynamic commission and pricing logic | Done
381 | Category/store/product-level configurability | Done
382 | Premium customer-facing UI | Done
383 | Search-heavy product/store discovery | Done
384 | Smart recommendations and add-on selling | Partial / in progress
385 | Configurable homepage and advertising support | Done
386 | Full order lifecycle visibility | Partial / in progress
387 | Flexible cancellation / refund / replacement workflows | Done
388 | Real-time notifications and post-order engagement | Partial / in progress
389 | Scheduled orders and seller-driven future/pre-book product publishing | Done
390 | Flexible logistics participation model for sellers | Done
391 | Seller settlement and payout handling | Not Done
392 | Admin-assisted product listing and seller shop setup | Done
393 | Scalable architecture for multi-city, high-traffic operations | Partial / in progress
394 | Clear role-based separation across Customer, Seller, Admin, and operational modules with configurable, future-ready business rules | Partial / in progress

## Summary
Zinto Requirements — Progress Summary
Total Requirements | 394
Done | 220
Partial done | 32
Not Done | 138
% Complete | 55.84%